## Instructions
Instructions and assistance for TASK 2: Developing a Maintenance Strategy
Please note the various tabs on the bottom of the spreadsheet. You will find lots of useful information containted within these in addition to your sub-task templates.
Rank the projects in the project list into high, medium and low priority |  | Information location
Consider - | a) What category does the project fall into? | Project List & definitions
| b) How long is the outage duration? | Project List
| c) Has the project already started? | Project List
| d) What are the project costs to date? | Project List
Once you have an agreed prioritised project list develop the project schedule
Consider - | a) What fuel powers the station, is there a better time to schedule the outage?
| b) Barron, Kareeya and Koombooloomba are all supplied by water falling into the rivers | Rainfall charts
c) Wivenhoe and Swanbank are not impacted by rain levels but more so by electricity prices which are lower in spring and autumn (Remember: seasons may be different in Queensland compared with where you are from (i.e. Northern Hemisphere vs. Southern Hemisphere)
| d) Are there any network outages being conducted in the year? | Outage list
| e) Each power station has a different output, avoid overlapping outages between Wivenhoe and Swanbank. | Definitions
You now need to make a 10% project costs saving for FY22 (financial year ending June 2022). Present your savings and justifications (Use "1. Project list" to do this)
Consider - | What are the projects that can be cancelled or deferred? | Project List
DELIVERABLES for TASK 2
1. Update the project list for priority, recommendations and justifications
2. Complete the Project Outage request form with your scheduled outage dates, including any with no impact to production (i.e. 0 days outage duration)

## Definitions
Category | Description | Station | Number of units | MW output | Factsheets for your Information
Approval Status | Status of the project | Barron Gorge | 2 | 66 | Factsheet_Barron-Gorge.pdf
Approved (1 Appraise) | Project has been approved but has not yet started, normally low or no spend to date | Kareeya | 4 | 88 | Factsheet_Kareeya.pdf
Approved (3 Define) | Project is approved and in design phase | Koombooloomba | 1 | 7 | Factsheet_Koombooloomba.pdf
Approved (4 Execute) | Project is approved and in execution phase, materials may have been ordered and site work may be underway. | Swanbank | 1 | 385 | Factsheet_Swanbank-E.pdf
Asset Life | Expected life of the asset or project. i.e. overhauls are conducted every 4 years | Wivenhoe | 2 | 570 | Factsheet_Wivenhoe.pdf
Budgeted Start Date | Financial year the project was expected to be approved and commenced. May not be complete in the same year.
Emergency | Unplanned and unbudgeted project usually as a result of failure or damaging event (i.e. lightning, flood, storms etc)
End of life | Asset has reached the end of its useful life, likely to have a reduction in performance and reliability
Forecast spend FY21 | forecast spend in financial year 21. i.e. From 1 July 2020 through to 30 June 2021
Forecast spend FY22 | forecast spend in financial year 22. i.e. From 1 July 2021 through to 30 June 2022
Growth | Opportunity that adds value to the portfolio through additional revenue
Improvement | Opportunity to improve the way an asset operates; this could be through better efficiency of the asset or a better way to operate and maintain
In-Service Date | Date the asset is required to be inservice by
Maintenance | Routine maintenance based on asset life plan
Not Started | Unapproved project
Obsolescence | Asset is no longer supported by the manufacturer. May not impact on performance.
Outage Duration | Number of days the asset (unit or station) needs to be out of service to complete the project
Portfolio | Site the project is based on
Project | Description of the project
Project Category | Project category
Project spend to date | Actual project spend so far on the project
Spares | Spare parts
Unit | Associated unit for the project i.e. Wivenhoe unit 1 overhaul, only inpacts unit 1

## 1. Project list
DELIVERABLE #1
a) Rank the projects in the project list into high, medium and low priority (Column M) Top tip: First, filter projects in the APPROVED (4 Execute) phase. These costs are already spent & budgeted for & will help with your decision making process.
b) Recommendations (fill in Column N)
c) Assess and update columns N & O where you can provide justification for your 10% project cost savings
Portfolio (Asset) | Project Category | Outage Duration | Unit | Project | Approval Status | Asset Life | Budgeted Start Date | In-Service Date | Project spend to date | Forecast spend FY21 | Forecast spend FY22 | Priority | Recommendation Proceed/Defer/Cancel | Justification
Wivenhoe | Maintenance | 99 | 1 | Major Overhaul | Approved (3 Define) | 4 | FY20 | 2022-02-28 | 449416.135 | 367934.4636 | 25326029.8128 | HIGH | PROCEED
Wivenhoe | Maintenance | 45 | 1 | W1 Guard Gate Modifications | Approved (4 Execute) | 30 | FY20 | 2022-01-31 | 497784.51 | 412936.9144 | 6135881.0701 | HIGH | PROCEED
Wivenhoe | Maintenance | 3 | Site | Splityard Re-Water Valve Modifications | Not Started | 10 | FY20 | 2023-07-31 | 0 | 0 | 42730.4072 | LOW | DEFER
Wivenhoe | Improvement | 1 | Both | Stator Short Circuit Switch Units 1&2 | Approved (3 Define) | 10 | FY21 | 2021-07-31 | 47001.36 | 10105.0808 | 41086.93 | MEDIUM | PROCEED AS PER BUDGET
Wivenhoe | Improvement | 0 | Site | Install and Upgrade VESDA Fire Detection | Not Started | 15 | FY21 | 2021-11-30 | 0 | 0 | 188999.878 | MEDIUM | PROCEED AS PER BUDGET
Wivenhoe | Improvement | 0 | Site | Battery Room Fire Suppression | Not Started | 10 | FY20 | 2022-06-30 | 0 | 12631.25 | 0 | HIGH | PROCEED
Wivenhoe | Improvement | 0 | Site | Silo 1 and 2 Lift Controller Replacement | Approved (4 Execute) | 20 | FY20 | 2021-12-31 | 66594.395 | 231467.6562 | 0 | MEDIUM | PROCEED AS PER BUDGET
Wivenhoe | Maintenance | 0 | Site | Fire (Smoke) Door and Actuation | Approved (4 Execute) | 10 | FY20 | 2021-10-31 | 0 | 113339.701 | 0 | HIGH | PROCEED
Wivenhoe | Maintenance | 15 | Both | Replace Operating Air Driers | Not Started | 15 | FY21 | 2022-01-31 | 0 | 0 | 123260.79 | HIGH | PROCEED
Wivenhoe | Maintenance | 30 | Both | Splityard Bulkhead Refurbishment | Not Started | 15 | FY20 | 2022-01-31 | 0 | 0 | 205434.65 | MEDIUM | PROCEED AS PER BUDGET
Wivenhoe | Maintenance | 0 | Site | Repaint Admin Area Buildings | Not Started | 15 | FY21 | 2021-11-30 | 0 | 0 | 100662.9785 | LOW | CANCEL
Wivenhoe | Improvement | 0 | Site | Plant Drain System - Replace Valves | Not Started | 15 | FY21 | 2022-06-30 | 0 | 0 | 127554.3742 | MEDIUM | PROCEED
Wivenhoe | Obsolescence | 10 | Both | Local Control Panel Replacement | Not Started | 15 | FY20 | 2022-02-28 | 0 | 0 | 92445.5925 | LOW | DEFER
Wivenhoe | End of life | 40 | Site | Replace Splityard Main Switchboard | Not Started | 15 | FY20 | 2021-03-31 | 0 | 15763.8 | 0 | LOW | PROCEED
Wivenhoe | Improvement | 0 | Site | Review and Modelling of Wivenhoe Low Load Operations to improve operational efficiency | Not Started | 1 | FY20 | 2022-08-31 | 0 | 98523.75 | 421141.0325 | MEDIUM | PROCEED
Wivenhoe | Obsolescence | 8 | 2 | Control System Hardware Unit 2 | Approved (3 Define) | 10 | FY21 | 2021-11-30 | 25034.42 | 0 | 513586.625 | MEDIUM | PROCEED
Wivenhoe | Maintenance | 0 | Site | Parapet Roof Replacement | Not Started | 15 | FY20 | 2022-06-30 | 0 | 50525 | 0 | LOW | DEFER
Wivenhoe | Improvement | 0 | Site | Tailbay Boom Replacement | Approved (4 Execute) | 10 | FY20 | 2021-10-31 | 0 | 111155 | 0 | HIGH | PROCEED
Wivenhoe | Maintenance | 0 | Site | Access Track Re-Aligment | Not Started | 15 | FY21 | 2022-02-28 | 0 | 0 | 205434.65 | MEDIUM | PROCEED
Wivenhoe | Maintenance | 0 | Site | Cooling Water Tank Re-Line | Not Started | 20 | FY20 | 2021-11-30 | 0 | 0 | 164347.72 | MEDIUM | PROCEED
Wivenhoe | Improvement | 0 | Site | Replace Pontoon Boat Motor | Not Started | 15 | FY21 | 2021-08-31 | 0 | 0 | 41086.93 | MEDIUM | PROCEED
Wivenhoe | Obsolescence | 0 | Site | Emergency Diesel Generator Control Upgrade | Not Started | 15 | FY21 | 2021-10-31 | 0 | 0 | 176673.799 | LOW | DEFER
Wivenhoe | Improvement | 10 | Site | Remote Alarm Operating Interface | Approved (4 Execute) | 7 | FY20 | 2021-07-31 | 0 | 0 | 308151.975 | MEDIUM | PROCEED
Swanbank | Emergency | 32 | 1 | Steam Turbine HP Inner Casing Crack Rectification | Approved (4 Execute) | 15 | FY20 | 2021-08-31 | 3853.07 | 736199.775 | 4226407.0544 | HIGH | PROCEED
Swanbank | Maintenance | 0 | Site | Water Treatment Area Security Fence | Approved (4 Execute) | 15 | FY20 | 2021-07-31 | 0 | 50525 | 0 | MEDIUM | PROCEED
Swanbank | Improvement | 0 | Site | Fire Systems Improvement | Approved (4 Execute) | 5 | FY20 | 2021-07-31 | 0 | 12631.25 | 0 | MEDIUM | PROCEED
Swanbank | Improvement | 20 | 1 | GT operational flexibility modifications | Approved (4 Execute) | 13 | FY20 | 2021-07-31 | 573433.75 | 176837.5 | 749836.4725 | MEDIUM | PROCEED
Swanbank | Maintenance | 0 | Site | Picnic Area Toilets | Approved (4 Execute) | 25 | FY20 | 2021-04-30 | 0 | 41430.5 | 0 | LOW | DEFER
Swanbank | Improvement | 0 | Site | Re-route Weir Water Discharge | Not Started | 13 | FY20 | 2021-09-30 | 0 | 75787.5 | 0 | MEDIUM | PROCEED
Swanbank | Improvement | 0 | Site | Site Reconfiguration -Station Sewerage Plant | Not Started | 25 | FY20 | 2021-07-31 | 0 | 303150 | 0 | MEDIUM | PROCEED
Swanbank | Spares | 30 | 1 | Gas Turbine Components (compressor vane carrier etc) | Not Started | 13 | FY21 | 2023-07-31 | 0 | 0 | 4056907.0334 | MEDIUM | DEFER
Swanbank | Improvement | 0 | Site | Site Security Access and Cameras Upgrade | Not Started | 5 | FY20 | 2021-12-31 | 0 | 60630 | 205434.65 | MEDIUM | PROCEED
Swanbank | Maintenance | 5 | Site | Make up water improvements and pumps overhaul | Not Started | 5 | FY20 | 2021-08-31 | 0 | 25262.5 | 205434.65 | MEDIUM | PROCEED
Swanbank | End of life | 2 | 1 | Powerlink Secondary System Replacement Project | Approved (3 Define) | 13 | FY20 | 2023-07-31 | 0 | 37893.75 | 564945.2875 | MEDIUM | PROCEED
Swanbank | End of life | 2 | 1 | SAM Panel PLC Replacement | Approved (4 Execute) | 13 | FY20 | 2021-06-30 | 0 | 75787.5 | 0 | HIGH | PROCEED
Swanbank | Maintenance | 1 | 1 | Air intake weather hood replacement | Approved (4 Execute) | 13 | FY20 | 2021-05-31 | 0 | 75787.5 | 0 | HIGH | PROCEED
Swanbank | Improvement | 0 | Site | Improved monitoring of the lake | Not Started | 10 | FY20 | 2022-04-30 | 0 | 0 | 205434.65 | LOW | DEFER
Barron Gorge | Improvement | 5 | Site | Under sluice gate replacement | Not Started | 20 | FY20 | 2021-06-30 | 0 | 25262.5 | 0 | LOW | PROCEED
Barron Gorge | Maintenance | 5 | 2 | U2 Main Inlet Valve Overhaul FY20/21 | Not Started | 20 | FY21 | 2022-07-31 | 0 | 0 | 28760.851 | MEDIUM | PROCEED
Barron Gorge | Maintenance | 5 | Site | Weir Gate House Sluice Gate FY21/22 | Not Started | 20 | FY21 | 2022-06-30 | 0 | 0 | 61630.395 | MEDIUM | PROCEED
Barron Gorge | Obsolescence | 15 | Both | SCADA Upgrade FY20/21 | Approved (1 Appraise) | 15 | FY20 | 2021-10-31 | 0 | 454725 | 924455.925 | LOW | CANCEL
Barron Gorge | Growth | 2 | 1 | Synchronous Condenser | Approved (4 Execute) | 20 | FY20 | 2021-07-31 | 127865.72 | 191995.2223 | 0 | HIGH | PROCEED
Barron Gorge | Maintenance | 5 | 1 | Turbine thrust bearing coolers | Approved (4 Execute) | 20 | FY20 | 2021-06-30 | 54897.63 | 131365 | 0 | MEDIUM | PROCEED
Barron Gorge | Improvement | 0 | Site | Turbine Floor Sound Curtains | Not Started | 10 | FY21 | 2022-02-28 | 0 | 0 | 246521.58 | HIGH | PROCEED
Barron Gorge | Improvement | 1 | Both | EDG Synchroniser / LV Switching | Approved (3 Define) | 20 | FY20 | 2021-09-30 | 0 | 75787.5 | 0 | HIGH | PROCEED
Kareeya | Improvement | 0 | Site | Cable Car Major Upgrade FY19-22 | Not Started | 20 | FY20 | 2022-05-31 | 0 | 35367.5 | 821738.6 | HIGH | PROCEED
Kareeya | Emergency | 0 | Site | Land slip stabilisation Intake Road | Approved (4 Execute) | 10 | FY20 | 2021-07-31 | 59881.935 | 18626.5465 | 0 | HIGH | PROCEED
Kareeya | Maintenance | 0 | Site | Intake Access Road Reseal and Concrete Drains | Not Started | 10 | FY20 | 2022-07-31 | 0 | 126312.5 | 0 | MEDIUM | PROCEED
Kareeya | Improvement | 0 | Site | Replace / Upgrade Essential Services Shed | Approved (3 Define) | 25 | FY20 | 2021-09-30 | 0 | 0 | 780651.67 | HIGH | PROCEED
Kareeya | Improvement | 0 | Site | Upgrade network connectivity | Approved (1 Appraise) | 10 | FY20 | 2021-07-31 | 1000 | 126312.5 | 410869.3 | HIGH | PROCEED
Kareeya | Improvement | 10 | all | 22Kv tower replacement / upgrade | Not Started | 25 | FY21 | 2023-07-31 | 0 | 0 | 205434.65 | MEDIUM | DEFER
Kareeya | Emergency | 0 | Site | Replace and Upgrade Catenary Cable to Portal | Approved (4 Execute) | 20 | FY20 | 2021-11-30 | 91341.94 | 16717.2067 | 630684.3755 | HIGH | PROCEED
Kareeya | Maintenance | 0 | Site | Air conditioner Replacement | Approved (4 Execute) | 15 | FY20 | 2021-06-30 | 0 | 90945 | 0 | MEDIUM | PROCEED
Kareeya | End of life | 20 | all | Turbine Governor Control System | Approved (4 Execute) | 20 | FY20 | 2021-11-30 | 308775.655 | 332252.3242 | 2762229.1083 | MEDIUM | PROCEED
Koombooloomba | Improvement | 10 | 5 | Scada Replacement - K5-014 | Not Started | 10 | FY20 | 2021-08-31 | 0 | 65682.5 | 30815.1975 | MEDIUM | DEFER
Koombooloomba | Improvement | 5 | 5 | 22Kv Circuit Breaker Replacement - K5-011 | Not Started | 20 | FY21 | 2022-01-31 | 0 | 0 | 123260.79 | MEDIUM | PROCEED
Koombooloomba | Improvement | 0 | site | Fire detection system upgrade | Not Started | 15 | FY21 | 2022-06-30 | 0 | 0 | 41086.93 | MEDIUM | PROCEED
Koombooloomba | End of life | 5 | 5 | Protection Relay Replacement | Approved (4 Execute) | 15 | FY20 | 2021-06-30 | 55282.705 | 51152.0152 | 0 | HIGH | PROCEED
[9 empty] | 2362163.225 | 4838808.7061 | 51497048.3849

## 2. Project Outage Request
DELIVERABLE #2 - Project outage request form
Please fill this in. Revisit instructions tab and your resources to assist.
Station | Unit # | Unit production impacted (MW) | Reason / Detail | Date Out Of Service | Date Returned To Service | Duration
Barron Gorge | 1 & 2 | 66 | Powerlink works: Feeder outage at Station | 2021-06-14 | 2021-06-24 | 10
Swanbank E | 1 | 385 | ST HP Crack Repair outage to remove starts limitation | 2021-06-02 | 2021-07-12 | 40
|  |  | Unit 2 H012 MT. ENGLAND 824 WIVENHOE PS UNIT 2 275KV CB 8242 CT Calibration | 2021-07-07 | 2021-07-07 | 0
Wivenhoe |  |  | Unit 1 2021 Overhaul (2020 postponed) | 2021-07-12 | 2021-10-19 | 99
|  |  | Annual outage |  |  | 0
Wivenhoe | [5 empty] | 0
Kareeya | 2 | 22 | OOS - 5 yearly maintenance |  |  | 0
Wivenhoe | 1 | 0 | Major Overhaul | 2022-06-28 | 2022-07-30 | 33
Wivenhoe | 1 | 0 | WiGuard Gate Modifications | 2022-07-31 | 2022-07-31 | 1
Swanbank E
Wivenhoe | 1 & 2 | 0 | Stator Short Circuit Switch Units 1&2 | 2021-07-31 | 2021-07-31 | 1
Wivenhoe | 1 | 0 | Install and Upgrade VESDA Fire Detection | 2021-07-30 | 2021-07-31 | 1
Wivenhoe | 1 | 0 | Battery Room Fire Suppression | 2021-07-30 | 2021-07-31 | 1
Swanbank | 1 |  | SAM Panel PLC Replacement | 2021-07-30 | 2021-08-01 | 2
Swanbank | 1 |  | Air intake weather hood replacement | 2021-07-15 | 2021-07-16 | 1
Koombooloomba |  |  | Protection Relay Replacement | 2021-07-01 | 2021-07-05 | 5
Wivenhoe | 1 | 0 | Spitlyard Bulkhead Refurbishment | 2021-07-31 | 2021-07-31 | 1
Wivenhoe | 1 | 0 | Replace Admin Area Buildings | 2022-07-31 | 2022-07-31 | 1
Wivenhoe | 1 & 2 | 0 | Plant Drain System - Replace Valves | 2022-07-31 | 2022-07-31 | 1
Wivenhoe | 1 | 0 | Local Control Panel Replacement | 2022-07-31 | 2022-07-31 | 1
Kareeya | all |  | Turbine Governor Control System | 2021-07-01 | 2021-07-21 | 20
Wivenhoe | 1 | 0 | Review and Modelling of Wivenhoe Low Load Operations to Improve Efficiency | 2022-07-31 | 2022-07-31 | 1
Koombooloomba | 1 |  | 22Kv Circuit Breaker Replacement - K5-011 | 2024-02-01 | 2024-08-05 | 5
Wivenhoe | 1 | 0 | Parapet Roof Replacement | 2022-07-31 | 2022-07-31 | 1
Wivenhoe | 1 | 0 | Tailsbay Boom Replacement | 2022-07-31 | 2022-07-31 | 1
Wivenhoe | 1 | 0 | Access Track Re-Alignment | 2021-07-31 | 2021-07-31 | 1
Wivenhoe | 1 & 2 | 0 | Cooling Water Tank Re-Line | 2021-07-31 | 2021-07-31 | 1
Wivenhoe | 1 | 0 | Replace Pontoon Boat Motor | 2021-07-31 | 2021-07-31 | 1
Wivenhoe | 1 & 2 | 0 | Emergency Diesel Generator Control Upgrade | 2021-07-31 | 2021-07-31 | 1
Wivenhoe | 1 | 0 | Remote Alarm Operating Interfaces | 2021-08-01 | 2021-08-02 | 10

## Schedule view of outage request
Extension task: Schedule view of outage request
Note: This is a semi-populated suggestion of the outage request schedule. Feel free to use this as a guide. If you choose to fill this out, you will need to populate the number of units offiline, and when. Be consistent with colour coding.
| 2021 | [29 empty] | 2021 | [30 empty] | 2021 | [30 empty] | 2021 | [29 empty] | 2021 | [30 empty] | 2021
| June | [29 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November
 | time axis 2021-06-01 to 2021-11-30
Barron Gorge | bar: 2021-06-01 to 2021-06-30; 2021-08-01 to 2021-09-02; 2021-09-10; 2021-09-16; 2021-09-19; 2021-10-01 to 2021-10-31
Kareeya | bar: 2021-06-01 to 2021-06-30; 2021-07-26; 2021-08-01 to 2021-08-31; 2021-09-10; 2021-10-01 to 2021-10-31
Swanbank E | bar: 2021-06-01 to 2021-06-30; 2021-08-01 to 2021-08-31; 2021-10-01 to 2021-10-31
Wivenhoe | 2021-07-07: 2; 2021-07-12: 1; 2021-07-13: 1; 2021-07-14: 1; 2021-07-16: 1; 2021-07-25: 1; 2021-07-26: 1; 2021-08-05: 1; 2021-08-30: 1; 2021-08-31: 1; 2021-09-01: 1; 2021-09-02: 1; 2021-09-10: 1; 2021-09-11: 1; 2021-09-15: 1; 2021-09-16: 1; 2021-09-19: 1; 2021-10-05: 1; 2021-10-17: 1; 2021-10-19: 1
MW impacted | 2021-06-02: 385; 2021-06-14: 66; 2021-07-07: 285; 2021-07-12: 285; 2021-07-13: 285; 2021-07-14: 285; 2021-07-15: 570; 2021-07-16: 285; 2021-07-25: 285; 2021-07-26: 373; 2021-08-04: 285; 2021-08-05: 285; 2021-08-30: 318; 2021-08-31: 318; 2021-09-01: 318; 2021-09-02: 351; 2021-09-09: 373; 2021-09-10: 373; 2021-09-11: 351; 2021-09-12: 351; 2021-09-13: 351; 2021-09-14: 351; 2021-09-15: 351; 2021-09-16: 318; 2021-09-19: 318; 2021-10-05: 285; 2021-10-17: 285; 2021-10-18: 307; 2021-10-20: 22; 2021-10-21: 22; 2021-10-22: 473; 2021-10-31: 407; 2021-11-01: 407
MW
Units | 2021-06-01: 1; 2021-06-02: 2; 2021-06-03: 3; 2021-06-04: 4
Barron Gorge | 2021-06-01: 33; 2021-06-02: 33
Kareeya | 2021-06-01: 22; 2021-06-02: 22; 2021-06-03: 22; 2021-06-04: 22
Swanbank E | 2021-06-01: 385
Wivenhoe | 2021-06-01: 285; 2021-06-02: 285
Key
Breaks up months for easier visualistion
All units offline for that particular portfolio asset. E.g. see cell O7
Specific units offline identified with number. E.g. If only Unit 2 of Wivenhoe is scheduled for an outage, then only "2" will show.
MW impacted | 2021-06-01: This specifies how many MW become unavailable across the portfolio. You may use the formulas to assist with this calculation e.g. Check pre-filled formula for cell BE12. You will see that ALL of Kareeya units and Unit 1 from Wivenhoe are scheduled for an outage. This results in 373MW becoming unavailable within the portfolio.

## Barron Rainfall
Product code | Station Number | Year | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Annual
IDCJAC0001 | 31036 | 1896 | 396 | 511.3 | 612.9 | 680.2 | 52.6 | 3 | 2.5 | 36.1 | 28.7 | 27.4 | 113 | 48 | 2511.7
IDCJAC0001 | 31036 | 1897 | 169.7 | 201.9 | 293.6 | 123.4 | 60.7 | 162.1 | 47.5 | 18.3 | 24.4 | 27.2 | 19.6 | 195.6 | 1344
IDCJAC0001 | 31036 | 1898 | 335 | 385.8 | 821.4 | 214.5 | 83.5 | 18.7 | 31 | 124.4 | 0.5 | 5.1 | 18 | 71.4 | 2109.3
IDCJAC0001 | 31036 | 1899 | 234.3 | 253.4 | 1212.7 | 204.5 | 82.8 | 30.7 | 65.8 | 44.8 | 77.3 | 9.4 | 16.8 | 70.5 | 2303
IDCJAC0001 | 31036 | 1900 | 962.6 | 26.7 | 215.4 | 88.9 | 102.1 | 57.8 | 12.3 | 1.3 | 51.6 | 38.8 | 20.8 | 69.6 | 1647.9
IDCJAC0001 | 31036 | 1901 | 371 | 598.7 | 300.1 | 213.3 | 337.7 | 25.2 | 20.8 | 54.4 | 45.9 | 60.7 | 103.3 | 12.7 | 2143.8
IDCJAC0001 | 31036 | 1902 | 122 | 294 | 272.7 | 95.2 | 84.8 | 135.3 | 144.2 | 34.3 | 0 | 6.4 | 39.1 | 64.3 | 1292.3
IDCJAC0001 | 31036 | 1903 | 459.9 | 275.7 | 1061.9 | 578.4 | 56.3 | 16 | 34.3 | 46.2 | 14.8 | 28.2 | 118 | 393.9 | 3083.6
IDCJAC0001 | 31036 | 1904 | 149 | 88.4 | 590.1 | 324.8 | 51.3 | 0 | 3.8 | 32.6 | 8.1 | 48.5 | 2 | 356 | 1654.6
IDCJAC0001 | 31036 | 1905 | 806.7 | 154.2 | 125.5 | 250.8 | 154 | 73.9 | 36 | 76.5 | 0 | 8.8 | 33 | 13.2 | 1732.6
IDCJAC0001 | 31036 | 1906 | 186.9 | 281.1 | 405.3 | 107.8 | 142.2 | 125.5 | 70.4 | 72.8 | 70.7 | 13.4 | 230.2 | 211.8 | 1918.1
IDCJAC0001 | 31036 | 1907 | 515.6 | 280 | 120.7 | 64.8 | 265.5 | 123.2 | 7.6 | 19.5 | 23.6 | 6.7 | 39.6 | 657.1 | 2123.9
IDCJAC0001 | 31036 | 1908 | 569.9 | 185.2 | 631.4 | 122.8 | 82.6 | 7.4 | 166 | 59.7 | 38.3 | 173.3 | 41.1 | 43 | 2120.7
IDCJAC0001 | 31036 | 1909 | 651.5 | 95.5 | 332.9 | 122.2 | 36.8 | 66.8 | 20.3 | 66 | 3.8 | 90.7 | 209.8 | 480 | 2176.3
IDCJAC0001 | 31036 | 1910 | 838.7 | 477.3 | 433.3 | 450.3 | 110.4 | 190.1 | 0 | 91.3 | 32 | 45.5 | 93.6 | 309.2 | 3071.7
IDCJAC0001 | 31036 | 1911 | 997.2 | 698.8 | 1264.1 | 1840.7 | 48.4 | 13.6 | 19.2 | 0 | 0 | 0 | 7.9 | 32 | 4921.9
IDCJAC0001 | 31036 | 1912 | 84.6 | 291.3 | 410 | 95.9 | 152.9 | 231.8 | 29.5 | 83.8 | 16.4 | 86.6 | 43.2 | 34 | 1560
IDCJAC0001 | 31036 | 1913 | 810.7 | 635.3 | 655.2 | 231.2 | 217 | 21.5 | 5.8 | 3 | 5.1 | 51.1 | 0 | 486.4 | 3122.3
IDCJAC0001 | 31036 | 1914 | 769 | 471.6 | 407.6 | 232 | 138.8 | 103.7 | 23.9 | 121.7 | 95.8 | 78.6 | 107.8 | 129.4 | 2679.9
IDCJAC0001 | 31036 | 1915 | 72.7 | 129 | 69 | 70.7 | 51.3 | 50.9 | 93.2 | 0 | 0 | 5.6 | 32.2 | 169.2 | 743.8
IDCJAC0001 | 31036 | 1916 | 654.1 | 185.6 | 92.6 | 148.4 | 98.9 | 44.3 | 136.8 | 84.4 | 90.9 | 86.9 | 25.4 | 643.1 | 2291.4
IDCJAC0001 | 31036 | 1917 | 113.3 | 240.9 | 266.4 | 150.5 | 95 | 22.6 | 0 | 49.5 | 11.9 | 80 | 202.6 | 245.3 | 1478
IDCJAC0001 | 31036 | 1918 | 214.1 | 310.5 | 235.3 | 229.7 | 71.9 | 6.9 | 60.5 | 117.7 | 1 | 6.6 | 28 | 144.9 | 1427.1
IDCJAC0001 | 31036 | 1919 | 325.4 | 198 | 104.1 | 372.4 | 80 | 59.1 | 68.3 | 34.1 | 72.1 | 2.3 | 30 | 17.7 | 1363.5
IDCJAC0001 | 31036 | 1920 | 426.8 | 387.1 | 194.5 | 443.1 | 395.1 | 75.5 | 122.1 | 6.4 | 30.2 | 36.6 | 122.9 | 183.3 | 2423.6
IDCJAC0001 | 31036 | 1921 | 278.4 | 353 | 722.9 | 547.3 | 118.1 | 245.5 | 50.8 | 49.7 | 56.8 | 90.7 | 63.8 | 330.5 | 2907.5
IDCJAC0001 | 31036 | 1922 | 149.3 | 427.6 | 352.8 | 326.3 | 113.8 | 76.2 | 90.7 | 20.8 | 26.7 | 30.8 | 1.5 | 116.9 | 1733.4
IDCJAC0001 | 31036 | 1923 | 102.9 | 192.6 | 611.1 | 136.7 | 19.8 | 70.6 | 15.7 | 23.4 | 0 | 2.5 | 11.7 | 109.2 | 1296.2
IDCJAC0001 | 31036 | 1924 | 264.6 | 210.8 | 272.8 | 330.9 | 130.6 | 52.7 | 69.8 | 85.5 | 44.9 | 2.5 | 192.8 | 248 | 1905.9
IDCJAC0001 | 31036 | 1925 | 337 | 378.9 | 762.7 | 237.9 | 0 | 137.3 | 21.9 | 0 | 0 | 0 | 21.8 | 17.8 | 1915.3
IDCJAC0001 | 31036 | 1926 | 414.9 | 93.7 | 205.4 | 224.5 | 22.8 | 25.9 | 10.4 | 39.7 | 144.2 | 0 | 23.8 | 161.2 | 1366.5
IDCJAC0001 | 31036 | 1927 | 428.3 | 788.6 | 186.4 | 283.8 | 46.8 | 53.8 | 72.2 | 0 | 35.3 | 52.3 | 8.7 | 92.6 | 2048.8
IDCJAC0001 | 31036 | 1928 | 101.4 | 407.6 | 461.2 | 47.3 | 65.7 | 19.3 | 55.9 | 14 | 0 | 9.9 | 221.4 | 65.9 | 1469.6
IDCJAC0001 | 31036 | 1929 | 632.7 | 811.3 | 243.5 | 85.4 | 28.7 | 36 | 24.4 | 20.3 | 35.5 | 0 | 60.3 | 90.5 | 2068.6
IDCJAC0001 | 31036 | 1930 | 1192.4 | 320.8 | 197.7 | 32.8 | 177.7 | 46 | 64.2 | 9.2 | 25.4 | 366.1 | 29 | 159.1 | 2620.4
IDCJAC0001 | 31036 | 1931 | 413.2 | 133.1 | 163.3 | 303.6 | 110.7 | 163.4 | 44.2 | 33.6 | 21.1 | 131 | 85.4 | 327.4 | 1930
IDCJAC0001 | 31036 | 1932 | 755.6 | 121 | 360 | 10.9 | 322.8 | 42.6 | 52.9 | 81.8 | 8.4 | 4.3 | 29.5 | 319.5 | 2109.3
IDCJAC0001 | 31036 | 1933 | 155.6 | 709.6 | 272.8 | 545.4 | 98.6 | 146.1 | 18.8 | 101.3 | 52 | 39.4 | 211.5 | 232.8 | 2583.9
IDCJAC0001 | 31036 | 1934 | 679.4 | 665.9 | 702.1 | 258.4 | 102.1 | 57 | 43.2 | 20.8 | 50.2 | 53.1 | 112.2 | 0 | 2744.4
IDCJAC0001 | 31036 | 1935 | 238.2 | 276.5 | 788.4 | 85.7 | 211 | 18.8 | 160.3 | 53.8 | 0 | 186.6 | 86.1 | 12.9 | 2118.3
IDCJAC0001 | 31036 | 1936 | 375.5 | 832 | 262.8 | 224.3 | 140.9 | 250.7 | 55.4 | 0 | 152.1 | 9.4 | 37.2 | 189.5 | 2529.8
IDCJAC0001 | 31036 | 1937 | 190.6 | 125.7 | 329.1 | 144.3 | 40.4 | 0 | 52.8 | 25.3 | 39.9 | 19.8 | 92 | 111.2 | 1171.1
IDCJAC0001 | 31036 | 1938 | 655.6 | 380.5 | 18.8 | 21.8 | 62.5 | 54.4 | 33 | 0 | 0 | 85.1 | 65.5 | 49.8 | 1427
IDCJAC0001 | 31036 | 1939 | 525 | 755.4 | 1100.8 | 159.5 | 37.6 | 165.1 | 6.6 | 17.3 | 4.3 | 41.1 | 81.8 | 18.8 | 2913.3
IDCJAC0001 | 31036 | 1940 | 389.6 | 652.8 | 1084.1 | 101.7 | 60.4 | 144.2 | 37.3 | 17.4 | 7.6 | 15.7 | 123.7 | 14.7 | 2649.2
IDCJAC0001 | 31036 | 1941 | 334 | 777 | 337.1 | 610.9 | 151.4 | 8.1 | 9.7 | 33 | 4.6 | 0 | 127.5 | 121.9 | 2515.2
IDCJAC0001 | 31036 | 1942 | 71.6 | 230.3 | 158 | 206.5 | 202.1 | 163.9 | 30.9 | 7.9 | 76.7 | 9.4 | 75.5 | 474.5 | 1707.3
IDCJAC0001 | 31036 | 1943 | 124.5 | 630.7 | 167.5 | 69.8 | 38.4 | 29.7 | 2.6 | 0 | 101 | 28 | 9.4 | 104.9 | 1306.5
IDCJAC0001 | 31036 | 1944 | 106.4 | 691.5 | 272.7 | 92.2 | 10.7 | 124.2 | 99.4 | 30.1 | 81.8 | 56.2 | 29.7 | 121.8 | 1716.7
IDCJAC0001 | 31036 | 1945 | 564 | 853.6 | 1297.5 | 207.9 | 205.3 | 68.3 | 90.9 | 5.6 | 1.3 | 22.9 | 40.2 | 263.5 | 3621
IDCJAC0001 | 31036 | 1946 | 280.4 | 496.4 | 214.7 | 21.6 | 65 | 32.7 | 30.3 | 3 | 2.6 | 8.4 | 22.4 | 24.9 | 1202.4
IDCJAC0001 | 31036 | 1947 | 94.1 | 504.2 | 302.5 | 120.2 | 129.2 | 68.8 | 51.8 | 219 | 90.9 | 70.9 | 109 | 39.3 | 1799.9
IDCJAC0001 | 31036 | 1948 | 512.5 | 159.3 | 360.7 | 84.7 | 49 | 139.1 | 112.4 | 64 | 0 | 0 | 29.2 | 156.7 | 1667.6
IDCJAC0001 | 31036 | 1949 | 348 | 574.5 | 454 | 358.3 | 63.1 | 15.3 | 9.8 | 74.7 | 25.4 | 2.5 | 50.4 | 132.4 | 2108.4
IDCJAC0001 | 31036 | 1950 | 722.5 | 336.6 | 433.4 | 459.9 | 53.7 | 76.6 | 103.8 | 0.5 | 22.9 | 33.5 | 382.1 | 548 | 3173.5
IDCJAC0001 | 31036 | 1951 | 400.8 | 67.5 | 145.5 | 17.6 | 48.6 | 43.5 | 18.1 | 28.5 | 134.1 | 51.2 | 68.3 | 9.9 | 1033.6
IDCJAC0001 | 31036 | 1952 | 484.4 | 180.1 | 267.6 | 153.7 | 94.5 | 14.4 | 21.1 | 97.2 | 37.9 | 49 | 38.5 | 41.5 | 1479.9
IDCJAC0001 | 31036 | 1953 | 941.2 | 265.1 | 682 | 254.5 | 58.4 | 35.8 | 90.5 | 43.5 | 133.8 | 16.5 | 54.9 | 125.9 | 2702.1
IDCJAC0001 | 31036 | 1954 | 228.4 | 327.8 | 316.3 | 287.6 | 76.2 | 95.7 | 41.2 | 108.7 | 11.1 | 120.7 | 18.2 | 51.7 | 1683.6
IDCJAC0001 | 31036 | 1955 | 96.5 | 922.1 | 681.3 | 205.8 | 187.5 | 177.7 | 25.2 | 24.2 | 66.3 | 55.6 | 133.1 | 30.2 | 2605.5
IDCJAC0001 | 31036 | 1956 | 440.1 | 267 | 543.8 | 155.1 | 46.4 | 46.2 | 21.1 | 29 | 26.2 | 34.8 | 36.2 | 322.5 | 1968.4
IDCJAC0001 | 31036 | 1957 | 686.5 | 385 | 501.7 | 116.9 | 142.8 | 130.1 | 39.7 | 0 | 0.8 | 14.5 | 80.3 | 57.4 | 2155.7
IDCJAC0001 | 31036 | 1958 | 347.9 | 527.1 | 520.7 | 251 | 114.5 | 79.7 | 0 | 41.4 | 8.4 | 2.3 | 53.4 | 87.9 | 2034.3
IDCJAC0001 | 31036 | 1959 | 541.3 | 299.4 | 804.2 | 176.9 | 173.8 | 121.3 | 48 | 118.1 | 79.4 | 0 | 72.1 | 286.7 | 2721.2
IDCJAC0001 | 31036 | 1960 | 651.3 | 276.9 | 370 | 47 | 26.4 | 62.1 | 77.7 | 10.3 | 1 | 19.6 | 15 | 53.3 | 1610.6
IDCJAC0001 | 31036 | 1961 | 168.6 | 62.2 | 303.5 | 169.6 | 117 | 8.1 | 19.9 | 18.3 | 25.3 | 26.6 | 47.5 | 111.4 | 1078
IDCJAC0001 | 31036 | 1962 | 503.4 | 478.4 | 144 | 140.1 | 15.5 | 109 | 85.7 | 17.5 | 128.1 | 0 | 28.9 | 37.5 | 1688.1
IDCJAC0001 | 31036 | 1963 | 581.7 | 959.4 | 242.4 | 524.7 | 131.9 | 30.1 | 8.9 | 13 | 10.9 | 65 | 41.9 | 114.4 | 2724.3
IDCJAC0001 | 31036 | 1964 | 436.1 | 393.7 | 732.6 | 121 | 408.2 | 10.2 | 32.5 | 22.2 | 95.4 | 136 | 75.7 | 296.7 | 2760.3
IDCJAC0001 | 31036 | 1965 | 198.3 | 376.5 | 417 | 242.4 | 184.2 | 204.5 | 23.6 | 7.2 | 2.8 | 54.4 | 37.2 | 175.3 | 1923.4
IDCJAC0001 | 31036 | 1966 | 215.7 | 83.6 | 231.8 | 124.8 | 68.6 | 73.8 | 16.8 | 64.5 | 0 | 11.3 | 59.2 | 71.1 | 1021.2
IDCJAC0001 | 31036 | 1967 | 57.5 | 550 | 991.5 | 156.5 | 172.4 | 113.2 | 51.9 | 13.3 | 0 | 41.3 | 98.1 | 37.5 | 2283.2
IDCJAC0001 | 31036 | 1968 | 559.6 | 794.1 | 144 | 220.1 | 122.6 | 10.2 | 63.1 | 23.9 | 16.5 | 9.9 | 25 | 43.1 | 2032.1
IDCJAC0001 | 31036 | 1969 | 780.6 | 221.6 | 427.3 | 70.7 | 92 | 99.3 | 213 | 30 | 41.9 | 39.7 | 10.9 | 145 | 2172
IDCJAC0001 | 31036 | 1970 | 142 | 459.2 | 679.5 | 182.1 | 48.2 | 38.7 | 21.6 | 69.3 | 10.2 | 31.5 | 245 | 195.7 | 2123
IDCJAC0001 | 31036 | 1971 | 62.8 | 515.3 | 893 | 587 | 30.2 | 47 | 20 | 16 | 4 | 7.7 | 103.3 | 142 | 2428.3
IDCJAC0001 | 31036 | 1972 | 596.3 | 804.6 | 743.7 | 97.4 | 143 | 113.2 | 2.5 | 12 | 127.9 | 0 | 32.5 | 35.8 | 2708.9
IDCJAC0001 | 31036 | 1973 | 80.2 | 391 | 635.2 | 463.1 | 81.3 | 105.5 | 37.5 | 16.1 | 47.1 | 73.7 | 240.4 | 654.8 | 2825.9
IDCJAC0001 | 31036 | 1974 | 292.9 | 832.8 | 802.2 | 65 | 125 | 11.4 | 4 | 31 | 30.5 | 13 | 53.4 | 295 | 2556.2
IDCJAC0001 | 31036 | 1975 | 189.2 | 532 | 256.8 | 180 | 75.4 | 111 | 75 | 31 | 114 | 154.8 | 132 | 768.3 | 2619.5
IDCJAC0001 | 31036 | 1976 | 130.2 | 442 | 287.4 | 189.4 | 25 | 8 | 10 | 10 | 10 | 17 | 30 | 484.5 | 1643.5
IDCJAC0001 | 31036 | 1977 | 345 | 994.5 | 865 | 456 | 174 | 60.8 | 34 | 95 | 56 | 27 | 50.4 | 85.6 | 3243.3
IDCJAC0001 | 31036 | 1978 | 544 | 210.8 | 164 | 86 | 121 | 5 | 8 | 43 | 15 | 138.5 | 99.1 | 164.7 | 1599.1
IDCJAC0001 | 31036 | 1979 | 2940 | 575 | 593.8 | 171.4 | 85 | 131.1 | 33.4 | 34.5 | 17.4 | 17.2 | 4.7 | 54 | 4657.5
IDCJAC0001 | 31036 | 1980 | 162.5 | 396.7 | 340.5 | 124.5 | 121 | 78 | 35 | 109 | 0 | 20.5 | 28 | 106 | 1521.7
IDCJAC0001 | 31036 | 1981 | 1341.5 | 537 | 93 | 74 | 175 | 7 | 110 | 0 | 48.5 | 33 | 166 | 68.4 | 2653.4
IDCJAC0001 | 31036 | 1982 | 134 | 120 | 405 | 309 | 47 | 21.5 | 3 | 111.5 | 6 | 9 | 88 | 49 | 1303
IDCJAC0001 | 31036 | 1983 | 71 | 8.5 | 612 | 98 | 294 | 12 | 26 | 95.5 | 107 | 91 | 82.5 | 82 | 1579.5
IDCJAC0001 | 31036 | 1984 | 171 | 476 | 317 | 106 | 56 | 35 | 69 | 7 | 0 | 48 | 155 | 117 | 1557
IDCJAC0001 | 31036 | 1985 | 615 | 687.5 | 566 | 235 | 110.6 | 18.2 | 13 | 15.5 | 10.4 | 91 | 113.5 | 43.5 | 2519.2
IDCJAC0001 | 31036 | 1986 | 434 | 266 | 202 | 333 | 90 | 69 | 52.5 | 48.5 | 16 | 39 | 71 | 55 | 1676
IDCJAC0001 | 31036 | 1987 | 126 | 661 | 121 | 313 | 97 | 160 | 101 | 38 | 61 | 32 | 64 | 161 | 1935
IDCJAC0001 | 31036 | 1988 | 65 | 149 | 320 | 72 | 117 | 18 | 85 | 59 | 62 | 30 | 181 | 305 | 1463
IDCJAC0001 | 31036 | 1989 | 236 | 2.5 | 8.2 | 580 | 21.3 | 9.7 | 23.1 | 7 | 11 | 0 | 42.8 | 171 | 1112.6
IDCJAC0001 | 31036 | 1990 | 138 | 27 | 663 | 267 | 277 | 102 | 26 | 0 | 77 | 16 | 20 | 316 | 1929
IDCJAC0001 | 31036 | 1991 | 681 | 762 | 72 | 96.5 | 117 | 34 | 52 | 14 | 0 | 3 | 36 | 88 | 1955.5
IDCJAC0001 | 31036 | 1992 | 99 | 265 | 122 | 201 | 184 | 9 | 49 | 37 | 16 | 16 | 7 | 444 | 1449
IDCJAC0001 | 31036 | 1993 | 482 | 234 | 39 | 255 | 95 | 110 | 95 | 39 | 93.5 | 22 | 44.5 | 157 | 1666
IDCJAC0001 | 31036 | 1994 | 452 | 606 | 60 | 215 | 58 | 56 | 134 | 46 | 35 | 22.5 | 25 | 9.1 | 1718.6
IDCJAC0001 | 31036 | 1995 | 119.8 | 745.9 | 755 | 18.5 | 160 | 118 | 21.7 | 232 | 9 | 83 | 45 | 89 | 2396.9
IDCJAC0001 | 31036 | 1996 | 358 | 269 | 687 | 185 | 108 | 96 | 52 | 14 | 11 | 256 | 60 | 390 | 2486
IDCJAC0001 | 31036 | 1997 | 430 | 508 | 540 | 66 | 28.5 | 70 | 40 | 96.5 | 99 | 52.5 | 121 | 476.5 | 2528
IDCJAC0001 | 31036 | 1998 | 398.2 | 514.5 | 153.5 | 171 | 120.5 | 45 | 57.5 | 156 | 142.5 | 88.5 | 190 | 242 | 2279.2
IDCJAC0001 | 31036 | 1999 | 261.5 | 1104 | 734 | 254 | 33.5 | 40 | 58 | 68 | 94.5 | 55.5 | 259 | 180 | 3142
IDCJAC0001 | 31036 | 2000 | 114 | 1531.5 | 499.5 | 517 | 108 | 50.5 | 7 | 81 | 13.5 | 49.5 | 224.5 | 607 | 3803
IDCJAC0001 | 31036 | 2001 | 255 | 890 | null | 223 | 5 | 137 | 8 | 18 | 25 | 95 | 108 | 15 | null
IDCJAC0001 | 31036 | 2002 | 91.5 | 360.5 | 77.5 | 135 | 114 | 4.5 | 7 | 77 | 3 | 0 | 28 | null | null
IDCJAC0001 | 31036 | 2003 | 245 | 198 | 231.5 | 208 | 108.4 | 58.5 | 60 | 44.5 | 10 | 17 | 27.5 | 215.5 | 1423.9
IDCJAC0001 | 31036 | 2004 | 262 | 728.5 | 1296 | 278 | 65 | 51.5 | 71 | 10 | 10 | 36 | 70 | 273 | 3151
IDCJAC0001 | 31036 | 2005 | 474 | 135.5 | 380.5 | 238.5 | 40 | 64 | 114 | 143.5 | 4 | 29 | 35 | 73 | 1731
IDCJAC0001 | 31036 | 2006 | 376 | null | 665 | 932 | 64.5 | 158.5 | 76 | 24 | 147 | 151 | null | null | null
IDCJAC0001 | 31036 | 2007 | 272.5 | 835.5 | 240 | 124 | 98.5 | null | 24.5 | 37 | 6 | 67 | 89.5 | 580 | null
IDCJAC0001 | 31036 | 2008 | 513.5 | null | 909 | 15.5 | 48 | 38 | 91 | 9.5 | 51.5 | 98 | 142 | 170 | null
IDCJAC0001 | 31036 | 2009 | 837 | 552 | 174 | 153 | 109 | 12 | 17 | 12 | 6.5 | 37 | 245 | 101 | 2255.5
IDCJAC0001 | 31036 | 2010 | 780 | 270.5 | 516 | 254.5 | 40 | 16 | 66 | 93 | 107 | 229.5 | 154.5 | 462 | 2989
IDCJAC0001 | 31036 | 2011 | 550.5 | 856 | 504 | 155.5 | 31 | 84 | 37 | 23 | 32.5 | 305 | 77 | 176 | 2831.5
IDCJAC0001 | 31036 | 2012 | 309 | 218 | 875 | 289 | 224.5 | 32.5 | 99 | 17.5 | 8.5 | 48 | 30 | 52 | 2203
IDCJAC0001 | 31036 | 2013 | 585.5 | 120 | 274 | null | 205 | 41 | 80 | 8 | 58 | 53 | 253 | 76.5 | null
IDCJAC0001 | 31036 | 2014 | 334 | 595 | 508 | 547 | 133 | 100 | 40 | 54.5 | 4 | 14 | 32 | 98 | 2459.5
IDCJAC0001 | 31036 | 2015 | 296.5 | 603.5 | 369 | 78 | 53 | 267.5 | 35.5 | 29 | 42 | 87.5 | 88 | 493 | 2442.5
IDCJAC0001 | 31036 | 2016 | 121.5 | 101.5 | 244 | 135 | 215.5 | 154 | 146 | 62 | 49 | 56.5 | 24 | 91 | 1400
IDCJAC0001 | 31036 | 2017 | 386 | 423 | 126 | 183.5 | 90 | 63 | 102 | 3 | 31.5 | 233 | 115 | 38 | 1794
IDCJAC0001 | 31036 | 2018 | 514.5 | 350 | 1216 | 64 | 57.5 | 64 | 60 | 4 | 14.5 | 23.3 | 66.3 | 1124.5 | 3558.6
IDCJAC0001 | 31036 | 2019 | 976.5 | 323 | 512.5 | 255 | 143.5 | 105.5 | 55 | 41.5 | 2.5 | 82.5 | 5.4 | 97.5 | 2600.4
IDCJAC0001 | 31036 | 2020 | 507.5 | 278.5 | 167.5 | 33 | 214.5 | 76.5 | 82 | 23.5 | 126.5 | 13.5 | 56.5 | 198.5 | 1778
IDCJAC0001 | 31036 | 2021 | 589.5 | 220 | 143 | null | null | null | null | null | null | null | null | null | null

## Kareeya Koombooloomba Rainfall
Product code | Station Number | Year | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Annual
IDCJAC0001 | 31083 | 1960 | null | null | null | null | null | null | null | null | null | null | 40.8 | 158.1 | null
IDCJAC0001 | 31083 | 1961 | 255.9 | 124.8 | 290 | 366.1 | 238.3 | 57.1 | 29.7 | 37.1 | 32.2 | 53 | 142.7 | 133.7 | 1760.6
IDCJAC0001 | 31083 | 1962 | 477.6 | 281.7 | 255.3 | 369.8 | 44.3 | 328.3 | 206.2 | 9.8 | 151.3 | 6.7 | 96.4 | 100.3 | 2327.7
IDCJAC0001 | 31083 | 1963 | 629.7 | 548.2 | 249.5 | 652.6 | 250.6 | 62.5 | 54.3 | 64.2 | 16.5 | 190.6 | 50.3 | 207 | 2976
IDCJAC0001 | 31083 | 1964 | 281.4 | 163.1 | 640.3 | 104.5 | 509.4 | 53.7 | 64.2 | 90.4 | 280.1 | 197.1 | 117.1 | 229.5 | 2730.8
IDCJAC0001 | 31083 | 1965 | 214.2 | 388 | 442.9 | 276 | 329.2 | 342 | 58.9 | 49.7 | 18.1 | 156.7 | 59.1 | 229.9 | 2564.7
IDCJAC0001 | 31083 | 1966 | 251.2 | 94.2 | 326.1 | 291.4 | 170 | 199 | 59.8 | 270.2 | 0.5 | 47.2 | 120.3 | 144.3 | 1974.2
IDCJAC0001 | 31083 | 1967 | 126.4 | 362 | 1390.7 | 322.2 | 446.7 | 194.2 | 158.1 | 63.1 | 0 | 118.7 | 121.4 | 82.6 | 3386.1
IDCJAC0001 | 31083 | 1968 | 409.5 | 705.5 | 251.8 | 138.2 | 132 | 30.1 | 150.4 | 24.5 | 30.3 | 68.7 | 37.9 | 44.9 | 2023.8
IDCJAC0001 | 31083 | 1969 | 608.8 | 416.7 | 416.5 | 176.9 | 114.3 | 178.3 | 417 | 69.9 | 70.4 | 94.1 | 12.3 | 214.6 | 2789.8
IDCJAC0001 | 31083 | 1970 | 69.1 | 413 | 416.4 | 344.8 | 140.1 | 105.1 | 102.9 | 110.1 | 16.9 | 87.5 | 331.3 | 160.1 | 2297.3
IDCJAC0001 | 31083 | 1971 | 179.5 | 421.2 | 847 | 783 | 51.7 | 53.1 | 112.5 | 26.4 | 31.3 | 106.7 | 102.7 | 125.9 | 2841
IDCJAC0001 | 31083 | 1972 | 378.5 | 786.2 | 672.8 | 220.8 | 298.5 | 184.1 | 19.6 | 31.5 | 178.5 | 0 | 9.6 | 20.9 | 2801
IDCJAC0001 | 31083 | 1973 | 216.5 | 366.9 | 630.2 | 771.9 | 219.4 | 212.7 | 102 | 38.7 | 101.9 | 155 | 285.5 | 635 | 3735.7
IDCJAC0001 | 31083 | 1974 | 400.6 | 674.1 | 736.4 | 306.7 | 320.8 | 42.7 | 7.6 | 36.2 | 89.2 | 39.8 | 104.2 | 67.8 | 2826.1
IDCJAC0001 | 31083 | 1975 | 291.9 | 667.4 | 566 | 414.3 | 119.4 | 162.4 | 275 | 143.4 | 377.6 | 71.6 | 142.8 | 267.2 | 3499
IDCJAC0001 | 31083 | 1976 | 203.1 | 449.7 | 237.3 | 402.3 | 188 | 175.8 | 114.4 | 34.6 | 11.4 | 51.8 | 121.1 | 108 | 2097.5
IDCJAC0001 | 31083 | 1977 | 242.2 | 1371.9 | 862.2 | 735.4 | 154.7 | 103.4 | 111.4 | 106.4 | 127.2 | 77.8 | 94 | 137.2 | 4123.8
IDCJAC0001 | 31083 | 1978 | 187.9 | 188.6 | 338.8 | 210.7 | 336.4 | 10.6 | 16.8 | 129 | 10.8 | 263.8 | 139.4 | 195.8 | 2028.6
IDCJAC0001 | 31083 | 1979 | 1867.6 | 709.4 | 413.6 | 265.6 | 286.4 | 220.3 | 120.6 | 38.4 | 62.2 | 18.4 | 6.4 | 120.6 | 4129.5
IDCJAC0001 | 31083 | 1980 | 88.8 | 120.8 | 676.4 | 384.7 | 245.4 | 121.7 | 115 | 382.4 | 0 | 60.2 | 62 | 196.6 | 2454
IDCJAC0001 | 31083 | 1981 | 789.2 | 786.6 | 247.1 | 179.8 | 315.2 | 13 | 172.4 | 3.8 | 373.3 | 136.4 | 170.9 | 112.3 | 3300
IDCJAC0001 | 31083 | 1982 | 226 | 299.9 | 378.4 | 703.7 | 183.8 | 68.9 | 22.2 | 284.5 | 41 | 18.5 | 96.3 | 181.5 | 2504.7
IDCJAC0001 | 31083 | 1983 | 62.4 | 91.7 | 338.3 | 234.8 | 455 | 104.8 | 106 | 207.1 | 145.2 | 27 | 87.6 | 142.9 | 2002.8
IDCJAC0001 | 31083 | 1984 | 277.6 | 659.4 | 281.1 | 163.6 | 242 | 276.2 | 184.2 | 22.3 | 0.2 | 84.6 | 162 | 94.4 | 2447.6
IDCJAC0001 | 31083 | 1985 | 251.3 | 723.3 | 677 | 323.8 | 267.8 | 45.5 | 62.6 | 15 | 72.6 | 253.6 | 133.3 | 73.4 | 2899.2
IDCJAC0001 | 31083 | 1986 | 633.9 | 536.4 | 370 | 435.8 | 184.4 | 181.8 | 55 | 51.6 | 36.6 | 48 | 53.2 | 36.4 | 2623.1
IDCJAC0001 | 31083 | 1987 | 37.2 | 422.4 | 163.2 | 593.6 | 295.8 | 386.4 | 114 | 54.4 | 151.2 | 31.8 | 121.6 | 90.8 | 2462.4
IDCJAC0001 | 31083 | 1988 | 114.6 | 262.8 | 446 | 186.6 | 167.6 | 90.2 | 213.4 | 220.6 | 109 | 161.6 | 316 | 397.2 | 2685.6
IDCJAC0001 | 31083 | 1989 | 286.4 | 143.2 | 849.5 | 520.5 | 470.5 | 115.6 | 109.4 | 9.2 | 25.8 | 26.8 | 290.4 | 212.4 | 3059.7
IDCJAC0001 | 31083 | 1990 | 113.2 | 81.6 | 708.8 | 274.8 | 515.2 | 171.6 | 51 | 0.8 | 158.2 | 0.6 | 7.8 | 388.2 | 2471.8
IDCJAC0001 | 31083 | 1991 | 586.6 | 818.6 | 104.4 | 258.2 | 302.4 | 98.8 | 70.8 | 40.2 | 0 | 2.2 | 132.6 | 93.6 | 2508.4
IDCJAC0001 | 31083 | 1992 | 101.2 | 241.2 | 105.2 | 313.6 | 319.2 | 22 | 181.4 | 49 | 33.6 | 19.2 | 29 | 317.2 | 1731.8
IDCJAC0001 | 31083 | 1993 | 325.9 | 282.8 | 45.2 | 367 | 319.2 | 252.8 | 311.6 | 114.6 | 160.8 | 25.8 | 70.4 | 171.2 | 2447.3
IDCJAC0001 | 31083 | 1994 | 360.8 | 461.4 | 170 | 341 | 223.4 | 101.4 | 223.4 | 168 | 39.2 | 43.6 | 35 | 113.2 | 2280.4
IDCJAC0001 | 31083 | 1995 | 187.4 | 437.4 | 379.6 | 49.4 | 211.8 | 293.2 | 35.2 | 596.8 | 33.8 | 138.6 | 135.4 | 98 | 2596.6
IDCJAC0001 | 31083 | 1996 | 301.2 | 276.2 | 797.7 | 225.4 | 291.8 | 198.2 | 111.9 | 52.2 | 1.7 | 272.6 | 31.4 | 406.4 | 2966.7
IDCJAC0001 | 31083 | 1997 | 421.9 | 411.3 | 723 | 409.3 | 72.8 | 128.9 | 142.9 | 84.5 | 77.3 | 7.2 | 40.7 | 358.9 | 2878.7
IDCJAC0001 | 31083 | 1998 | 718.8 | 272.8 | 277.4 | 265 | 274.4 | 136 | 137 | 25 | 241 | null | 205.8 | 248 | null
IDCJAC0001 | 31083 | 1999 | 249.7 | 707.7 | 967 | null | null | null | 90.2 | null | 143 | 67.6 | 209.6 | 330.2 | null
IDCJAC0001 | 31083 | 2000 | 129.5 | 1289.1 | 581 | 747.4 | 249 | 238.1 | 30.5 | 100 | 16 | 129.8 | 223.4 | 298.9 | 4032.7
IDCJAC0001 | 31083 | 2001 | 270.7 | 782.8 | 302 | 455.2 | 10.2 | 383.2 | 11 | null | null | 42.8 | null | 58 | null
IDCJAC0001 | 31083 | 2002 | 183.8 | 332.6 | 138.2 | 351.8 | 240.6 | 36 | 51.2 | 99 | 23.6 | 0 | 42.8 | 37.5 | 1537.1
IDCJAC0001 | 31083 | 2003 | 325 | 317.2 | 208.2 | 258 | 271 | 126.8 | 304.2 | 65.2 | 31.4 | 36.6 | 42 | 304 | 2289.6
IDCJAC0001 | 31083 | 2004 | 173.2 | 481.3 | 902.5 | 498.2 | 174.1 | null | 141.9 | null | null | 28.3 | 171 | 201.3 | null
IDCJAC0001 | 31083 | 2005 | 397 | 143.3 | 318.6 | 499 | 54 | 166 | 293 | 315 | 19 | 124.1 | 20.2 | 44 | 2393.2
IDCJAC0001 | 31083 | 2006 | 348.3 | 224.4 | 795.6 | null | null | 262 | 152 | 53 | 187.5 | 230 | null | 193 | null
IDCJAC0001 | 31083 | 2007 | 252 | null | 373 | 304 | 242 | 122 | 105 | 148 | 24 | 79 | 148 | 199 | null
IDCJAC0001 | 31083 | 2008 | 436 | null | 949 | 66 | 142 | 155 | 182 | 53 | 48 | 172 | 151 | null | null
IDCJAC0001 | 31083 | 2009 | 620.8 | 857 | 170 | 364.8 | 219.2 | 46 | 25 | 13.5 | null | 53 | 186 | 50 | null
IDCJAC0001 | 31083 | 2010 | 535 | 354.5 | 583.5 | 305 | 113.5 | 96 | 254 | 106 | 102.5 | 242 | 401.5 | 603 | 3696.5
IDCJAC0001 | 31083 | 2011 | 425.5 | 1020 | null | null | null | 221 | 113 | 113 | 61 | 364 | 104 | null | null

## Network outages
Region | Station Name | KV | Start Time | End Time | Impacted site
QLD1 | Barron Gorge Ps 132kV | 132 | 2021-06-14 08:00 | 2021-06-24 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2021-06-14 08:00 | 2021-06-24 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132/11 | 2021-06-14 08:00 | 2021-06-24 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2021-06-24 17:01 | 2021-09-02 11:59 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2021-09-02 12:00 | 2021-09-15 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2021-09-02 12:00 | 2021-09-15 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2021-09-15 17:01 | 2021-11-29 07:59 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2021-11-29 08:00 | 2021-12-06 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2021-11-29 08:00 | 2021-12-06 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2022-04-10 08:00 | 2022-04-20 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2022-04-10 08:00 | 2022-04-20 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132/11 | 2022-04-10 08:00 | 2022-04-20 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2022-04-20 17:01 | 2022-06-29 11:59 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2022-06-29 12:00 | 2022-07-12 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2022-06-29 12:00 | 2022-07-12 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2022-07-12 17:01 | 2022-09-25 07:59 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2022-09-25 08:00 | 2022-10-02 17:00 | Barron Gorge Ps
QLD1 | Barron Gorge Ps 132kV | 132 | 2022-09-25 08:00 | 2022-10-02 17:00 | Barron Gorge Ps
QLD1 | H51 Swanbank E | 275 | 2021-05-04 07:30 | 2021-05-04 16:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2021-05-04 07:30 | 2021-05-04 16:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2021-05-04 07:30 | 2021-05-04 16:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2021-05-05 07:30 | 2021-05-07 17:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2021-05-05 07:30 | 2021-05-07 17:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2021-05-05 07:30 | 2021-05-07 17:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2021-06-08 09:00 | 2021-06-08 15:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2021-06-16 08:00 | 2021-06-16 14:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2021-06-16 08:00 | 2021-06-16 14:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2021-06-16 08:00 | 2021-06-16 14:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-02-28 07:30 | 2022-02-28 16:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-02-28 07:30 | 2022-02-28 16:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-02-28 07:30 | 2022-02-28 16:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-03-01 07:30 | 2022-03-03 17:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-03-01 07:30 | 2022-03-03 17:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-03-01 07:30 | 2022-03-03 17:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-04-04 09:00 | 2022-04-04 15:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-04-12 08:00 | 2022-04-12 14:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-04-12 08:00 | 2022-04-12 14:00 | Swanbank E PS
QLD1 | H51 Swanbank E | 275 | 2022-04-12 08:00 | 2022-04-12 14:00 | Swanbank E PS
QLD1 | Kareeya Ps 132kV | 132/11/11 | 2021-07-28 08:30 | 2021-08-03 16:00 | Kareeya & Koombooloomba Power station
QLD1 | Kareeya Ps 132kV | 132/11/11 | 2021-08-05 07:00 | 2021-08-05 17:00 | Kareeya & Koombooloomba Power station
QLD1 | Kareeya Ps 132kV | 132/11/11 | 2022-05-24 08:30 | 2022-05-30 16:00 | Kareeya & Koombooloomba Power station
QLD1 | Kareeya Ps 132kV | 132/11/11 | 2022-06-01 07:00 | 2022-06-01 17:00 | Kareeya & Koombooloomba Power station
QLD1 | Mt. England 275kV | 275 | 2021-04-13 08:00 | 2021-04-13 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-04-13 08:00 | 2021-04-13 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-04-13 08:00 | 2021-04-13 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-04-14 08:00 | 2021-04-14 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-04-14 08:00 | 2021-04-14 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-04-14 08:00 | 2021-04-14 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-04-14 08:00 | 2021-04-14 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-04-14 08:00 | 2021-04-14 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-04-14 08:00 | 2021-04-14 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-05-11 09:00 | 2021-05-12 15:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-05-13 12:00 | 2021-05-13 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-05-14 08:00 | 2021-05-14 12:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-05-14 12:01 | 2021-05-14 15:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-05-25 10:00 | 2021-05-25 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-05-28 08:00 | 2021-05-28 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-08-17 07:31 | 2021-09-09 16:30 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-08-17 07:31 | 2021-09-09 16:30 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-08-17 07:31 | 2021-09-09 16:30 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-08-24 08:00 | 2021-08-24 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2021-08-24 08:00 | 2021-08-24 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-02-07 08:00 | 2022-02-07 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-02-07 08:00 | 2022-02-07 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-02-07 08:00 | 2022-02-07 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-02-08 08:00 | 2022-02-08 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-02-08 08:00 | 2022-02-08 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-02-08 08:00 | 2022-02-08 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-02-08 08:00 | 2022-02-08 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-02-08 08:00 | 2022-02-08 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-02-08 08:00 | 2022-02-08 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-03-07 09:00 | 2022-03-08 15:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-03-09 12:00 | 2022-03-09 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-03-10 08:00 | 2022-03-10 12:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-03-10 12:01 | 2022-03-10 15:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-03-21 10:00 | 2022-03-21 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-03-24 08:00 | 2022-03-24 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-06-13 07:31 | 2022-07-06 16:30 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-06-13 07:31 | 2022-07-06 16:30 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-06-13 07:31 | 2022-07-06 16:30 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-06-20 08:00 | 2022-06-20 16:00 | Wivenhoe PS
QLD1 | Mt. England 275kV | 275 | 2022-06-20 08:00 | 2022-06-20 16:00 | Wivenhoe PS
QLD1 | Swanbank E 275kV | 275 | 2021-05-04 07:30 | 2021-05-04 16:00 | Swanbank E PS
QLD1 | Swanbank E 275kV | 275 | 2021-05-05 07:30 | 2021-05-07 17:00 | Swanbank E PS
QLD1 | Swanbank E 275kV | 275 | 2021-06-07 08:00 | 2021-06-07 16:00 | Swanbank E PS
QLD1 | Swanbank E 275kV | 275 | 2022-02-28 07:30 | 2022-02-28 16:00 | Swanbank E PS
QLD1 | Swanbank E 275kV | 275 | 2022-03-01 07:30 | 2022-03-03 17:00 | Swanbank E PS
QLD1 | Swanbank E 275kV | 275 | 2022-04-03 08:00 | 2022-04-03 16:00 | Swanbank E PS
QLD1 | Swanbank E Ps | 275 | 2021-06-16 08:00 | 2021-06-16 14:00 | Swanbank E PS
QLD1 | Swanbank E Ps | 275 | 2022-04-12 08:00 | 2022-04-12 14:00 | Swanbank E PS
QLD1 | Tully 132kV | 132 | 2021-05-12 08:00 | 2021-05-12 16:00 | Kareeya & Koombooloomba Power station
QLD1 | Tully 132kV | 132 | 2021-05-13 08:00 | 2021-05-13 16:00 | Kareeya & Koombooloomba Power station
QLD1 | Tully 132kV | 132 | 2021-07-06 09:00 | 2021-07-07 16:00 | Kareeya & Koombooloomba Power station
QLD1 | Tully 132kV | 132 | 2022-03-08 08:00 | 2022-03-08 16:00 | Kareeya & Koombooloomba Power station
QLD1 | Tully 132kV | 132 | 2022-03-09 08:00 | 2022-03-09 16:00 | Kareeya & Koombooloomba Power station
QLD1 | Tully 132kV | 132 | 2022-05-02 09:00 | 2022-05-03 16:00 | Kareeya & Koombooloomba Power station